## Sheet1
Date(s) of Activity | Start/End Time of Activity | Type of Activity | Impact to Community/Public | District | Specific Location (Street to Street; between mile markers; etc.) | Notes / Comments
Highway Maintenance
6/10/24-6/14/24 | 8am-2pm | Shoulders Repairs | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | Hilo | Kaupakuea Hmstd Rd from Hwy 19 to Mauka Cross Country | Weather permitting
6/10/24-6/14/24 | 8am-2pm | Shoulder Mainteance | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | Puna | Ainaloa Blvd from Leilani Dr to Silversword | Weather permitting
6/10/24-6/14/24 | 8am-2pm | Shoulder Maintenance | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | Puna | KahakaiBlvd from Kikou St to Puni Makai | Weather permitting
6/10/24-6/14/24 | 8am-2pm | Shoulder Maintenance | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | N.Kohala | Akoni Puli Highway near 21.1 milemarker to 23.7 milemarker | Weather permitting
6/10/24-6/14/24 | 8am-2pm | Shoulder Maintenance | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | Kona | Nāpō'opo'o Rd from Hwy to End | Weather permitting
6/10/24-6/14/24 | 8am-2pm | Paving | Partial lane closure as needed; flaggers directing traffic; large trucks and personnel will be on the roadway. | Ka'u | Ka'alu'alu Road from HWY 11 to End | Weather permitting
Engineering
06/09/24 - 6/15/24 | 24 hours a day | Bridge Closed: Ka'ahakini Bridge & Kolekole Bridge | Detour - use Chin Chuck and Kanna Road. | Hamakua | Old Māmalahoa Hwy - just north of Kawiki Homestead Road & at Kolekole Beach Park.
06/09/24 - 6/15/24 | 24 hours a day | Bridge Closed: Kaiwilahilahi Bridge | Detour - use Pāpa‘aloa Avenue or Old Mamalahoa Highway. | Hamakua | Old Māmalahoa Hwy - between Pāpa‘aloa Country Store & Cafe/U.S. Post office and Pāpa‘aloa Hongwonji Mission
06/09/24 - 6/15/24 | 24 hours a day | Temporary Bridge Open: Makea Bridge | Detour route is closed. | So. Hilo | Kaupakuea Homestead Road - north of Andrade Rd. | Temporary Bridge Open.
06/09/24 - 6/15/24 | 24 hours a day | Pauahi Bridge | Half Bridge closed/Lane Shifts - One travel lane in each direction. | So. Hilo | Half Bridge closed/Lane Shifts - One travel lane in each direction.
06/010/24 - 6/14/24 | 7:00 am – 3:00 pm | Construction Project: Kilauea/Keawe Rehab., Ponahawai to Waiānuenue | No work | So. Hilo
06/010/24 - 6/14/24 | 8:30 am -3:00 pm | Construction Project: Lanikaula Street Rehab., Kilauea Ave to Manono St | Lane Shifts/closures. | So. Hilo | Lanikaula Street Rehab., Kilauea Ave. to Manono St.
06/010/24 - 6/14/24 | 8:30 am -3:00 pm | Construction Project: Māmalahoa Hwy Rehab., Kamalani Street to Kalamauka Road | Lane Shifts/closures. | Kona | Māmalahoa Hwy Rehab., Kamalani Street to Kalamauka Road
06/010/24 - 6/14/24 | 7:00 am -3:30 pm | Construction Project: Hilo Shipman Drywells Drainage Improvements | Lane Shifts | Keaau | Shipman Industrial Park: Williama Place, Melekahiwa Place, Melekahiwa Street, Mikahala Place
06/010/24 - 6/14/24 | 7:30 am -5:00 pm | Survey Work: Waipi`o Valley Road | Periodic road closures throughout the day. | Hamakua | Wapi`o Valley Road: Between the valley lookout to the beach access road.
06/010/24 - 6/14/24 | 8:30 am - 3:00 pm | Construction Project: Waiānuenue Ave. Rehab., Kaiulani Street to Rainbow Drive | Lane Shifts/closures. | So. Hilo | Waiānuenue Ave.: Between Komohana St. and Halai St.
06/010/24 - 6/14/24 | 8:00 am - 5:00 pm | Construction Project: Waikōloa Rehab. | Lane Shifts/closures | S. Kohala | Māmalahoa Highway 190 to Paniolo Avenue a. Ashalt Paving.
Traffic
06/10/2024 - 06/14/2024 | 8:30am - 2:00pm | Install pavement markings on resurfaced roadway | Expect officers directing traffic and minor delays. | S. Hilo | Kilauea Ave (between Puainako St & Haihai St) | Weather permitting
2024-06-10 | 8:30am - 2:00pm | Install pavement markings on resurfaced roadway | Expect officers directing traffic and minor delays. | Honokaa | Kalopā Mauka Rd | Weather permitting
2024-06-12 | 8:30am - 2:00pm | Install stop bars | Expect officers directing traffic and minor delays. | Honokaa | Lokelani St & Kukui St | Weather permitting
06/13/2024 - 06/14/2024 | 8:30am - 2:00pm | Install pavement markings on resurfaced roadway | Expect officers directing traffic and minor delays. | S. Hilo | Mauna Loa St | Weather permitting
06/10/2024 - 06/14/2024 | 8:00am -1:30pm | Install pavement markings on resurfaced roadway | Expect officers directing traffic and minor delays. | S. Kona | Nāpō'opo'o Rd | Weather permitting